## Sheet1
Harmonia Collaborative Care
2021 - 2024 Strategic Plan
Q1 2023 Update
Strategy | Tactic | Metrics | Resource | Timeline | Q1 2023 SP Progress Update | Q1 2023 Summary Notes | Q4 2022 Update
Goal 1: Programs and Services. Harmonia programs and services align with our vision, mission and core values supporting community need and meeting desired outcomes.
1.1: Program need is evidence-based, meets organizational mission, and is evaluated on a set of qualitative and quantitative measures. | 1.1.1: Assess community need and the link to the organization’s foundational elements. | Need is documented in business plans and tied back to organization mission. | Val, Program Leads, Magellan | Q1 - 2023 Updated to Q1-2024 | In process, but behind. Business plans for MH and SS are underway and set to be complete by end of summer. HH Bus Pl not yet started. Timeline updated 3/3/23. Process delayed due to recruitment issues in 2022. | Oishei Y1 monies expended; interim reporting completed 2/28/23. Awaiting Y2 funding in April. Currently providing 3 days at LSHS. ¦ Exhale: Pathways kick-off on 3/16. Two clinicians identified to lead support group. MH and SS are collaborating. ¦ Other opportunities need to be explored, such as Ovarian Cancer Project. ¦ HH continues to struggle with hiring into 2023. | School program expansion revised approach presented to Oishei. Oishei agreed to new direction and funded project for two-years. Currently providing two full days of student counseling. Additional full day added in January 2023. Two clinicians – three days. Implementing Year One of three-year Exhale grant in collaboration with Cradle Beach and Lisa Rood. Program incorporates Senior Services and Mental Health program areas. Open House, January 26 with March kick-off. March 2023 program Kick-off. MH Business Plan revisions in 2023. Begin Senior Program Plan – Seniors Services/CarePanion in 2023
| 1.1.2: Develop a set of processes and outcome measures across programs and services. | Performance measures cascade throughout program delivery – program, staff | Val, Michelle, Bev, Program leads, Magellan | Q4 - 2023 Revised to Q4 - 2024 | Performance measure development in process for MH - Quanitative through CCNY, qualitative not started; not started for SS or HH. Revised timeline 3/3/23. Process delayed due to hiring/recruitment in 2022 and not having a formal process for developing measures. | Megan is updating MH Clinic Manual. Megan has been trained on FormLab in 10e11 to update forms and chart structure in accordance with 599 Regs. ¦ Need to determine metrics (qualitative, satisfaction, HR, compliance and risk) across the org. Development process needs formal implementation. ¦ Consider: Should Goal 1 have a tactic to address regulatory standards which support the goal. This is not currently called out. | Megan working with consultant to develop clinic chart structure – new regs and requirements. Determining appropriate time and process to define metrics (qualitative, satisfaction, compliance and risk) across the organization.
1.2: Growth strategy considers organic, collaborative partnerships and mergers to sustainably and culturally address community need. | 1.2.1: Growth and expansion opportunities identified with a focus on sustainability and organizational foundational elements. | Growth strategies support mission and are fiscally viable. | Val, Program leads, BOD, Board Facilities Committee, Magellan | Q1 - 2024 | On track. Consider including strategy 1.2 into tactic 1.1.1. They are similar and this may not be a separate strategy or tactic. Discussion 3/3/23. Current metrics, sound like the business plan, identified in strategy 1.1. | No update on journal article. ¦ Opportunities for MH and SS are identified in tactic 1.1.1. ¦ HH on hold due to staffing issues. Stay the course. | Journal article – exploring potential to reinvigorate. MH expansion – reviewing opportunity to collaborate with other organizations and projects. Pathways to Caregivers – Exhale collaboration project
Goal 2: People Harmonia recruits, retains and develops the people to build organization strength, deliver quality programs and services and support our culture.
2.1: Staff Create a success-focused culture that promotes learning, discovery and achievement of our vision, mission | Tactic 2.1.1: Develop comprehensive organization structure, including organization chart, job descriptions and performance management processes that provide clear expectations tied to desired outcomes. | Staff clearly understand job expectations and are regularly evaluated on meeting expectations. | Val, Michelle, Bev, Atlas Align, Program leads, Magellan | Q1 – 2024 | On track. Much of this work has been completed. | Perfromance evaluations process and training in continued development. | On-going.
| Tactic 2.1.2: Develop staff recruitment processes founded in solid compensation and productivity models. | Organization uses appropriate models to support sustainable hiring | Val, Megan, Michelle, Program leads, Magellan | Q1 - 2022 | Making progress - new information regarding recruitment marketing requires new approach to application completion. Recruitment Plan drafted and processes associated with plan in refinement. | Alignment of compensation strategy & benefits (Employer Value Proposition) ¦ Budget for recruiting ¦ More scheduled communication with hiring managers to identify recruiting goals ¦ Formalized the recruiting process – full-cycle recruiting ¦ Identified more cost-effective advertising resources ¦ More effective use of our “Career Page” by adding fillable application (pending) ¦ Identifying metric to measure source and overall success or recruiting efforts – cost per hire, time to fill, turnover, etc. | On-going.
| Tactic 2.1.3: Create professional development process defined by program need and tied to expectations. | Staff are expected to participate in professional development opportunities. | Val, Bev, Program leads | Q4 – 2024 | On track. Considering as part of performance management process. | On-going - yearly | Performance management reviews completed for 2022.
2.2: People - Board of Directors Board provides good leadership and decision making approprate skill set and fiduciary oversight. | Tactic 2.2.1: Ensure board by-laws and related documents are updated to address legal requirements and meet the needs of the organization. | Yearly conflict of interest and Board member expectations are completed. | Board Chair, Governance Committee | Q4– 2022 | In Progress. By-Laws drafted and in review by attorney | By-Laws development led by CEO and in process of final draft by attorney. Slated to go before the BOD at April meeting | Follow-up with attorney on by-laws
| Tactic 2.2.2: Board committees are appropriate to the needs of the organization and offer the opportunity to reach out to non-board members with subject matter expertise. | Committees are active and membership is supportive of charter | Board Chair, Governance Committee | Q1 – 2023 | In Progress. Committees identified in By-Laws and open for Board discussion | Finalization of By-Laws includes establishment of Board committees and populating each | Marketing & Development Committee has new chair
| Tactic 2.2.3 Board focuses on retention of members dedicated to the mission and recruitment of new members within a defined skill set to support the organization. | Board evaluations and terms are conducted yearly and analyzed for need. | BOD, Governance Committee | Q2 - 2023 | On Track. Self-evaluation is part of pre-work for Board Retreat | Board Retreat is targeted for mid-June 2023. Board self-evaluation, population of Committees and review of Strategic Plan are on the agenda | Considering best approach to reach out to prospective board member candidate with clinical background
| Tactic 2.2.4: Board development plan is based on internal and external training. | Board training calendar | Board Chair, Governance Committee | Q4 – 2022 | Tactic timeline and content tobe re-evaluated at Retreat | Charting of Governance Committee is required to completed this tactic | Update to follow – discussion to consider in Board Retreat
Goal 3 – Fiscal Viability Harmonia embraces financial and data-driven growth and sustainability.
3.1: Harmonia is financially sustainable. | Tactics 3.1.1: Create a financial infrastructure to supports the accurate and timely preparation of financial statements in a format that satisfied the needs of different audiences (BOD, management) | Financial statements prepared in proper format. | Michelle, Val, Magellan, Chair of Finance Committee | Q4 – 2022 | Budget approved. | 2023 Budget reviewed with Program Managers. Previous meetings explained how budget was based and prepared for specific department. | 2023 Budget refined to include clinic service statistics and discussion of service area challenges and opportunitie
| Tactic 3.1.2: Business plans are supported through appropriate financial modeling, tied to financial expectations and inclusive of finance, marketing and operational considerations. | Contribution margin by program/service line. Key performance indicators – financial, marketing and operational | Val, Michelle, Program leads, Magellan | Q4 – 2023 | Business planning meetings will consider metrics. | KPIs to be determined in 2023 | Business Plan progress defined in Goal #1; KPIs to be considered in 2023
| Tactic 3.1.3 Develop and refine a MH recruitment model to support hiring decisions. Model includes estimates of direct revenue and fully loaded compensation costs. | Recruitment decisions help to ensure that new hires are fully utilized and fiscally profitable | Val, Megan, Michelle, Greg | Q1 2022 | Competed. MH Financial Recruitment model is completed | Will be meeting with Val, Greg and Megan in March to review for 2023 | On-going process
| Tactic 3.1.4 Develop and refine MH provider productivity model reporting revenue generated, fully loaded compensation costs and utilization of available time serving patients. | MH administration is improved based upon data | Val, Megan, Michelle, Greg | Q1 2022 | In Progress. Working with CCNY to identify how best to collect data from 10e11 and match it to financial reporting | Reports requested were sent to CCNY. Awaiting more information from them on productivity reporting and how they can help us | Confirmed need for productivity model that will benefit mental health in it’s provider time utilization and finance for provider profitability.
Strategy 3.2: Marketing & Development efforts engage grantors, major donors and contributors in financial support of our mission and vision. | Tactic 3.2.1: Marketing & communications plan is tied to engagement and support of organization | Awareness & engagement metrics | Val, Michelle, Magellan, Chair of Marketing & Development Committee | Q4 – 2022 | Compleed. Plan to develop awareness growing among funders and consumers in place. | Best Places to Work nomination promotion. Continuing recruitment - moving client marketing forward as more clinicians are hired. Pathways for Caregivers provides opportunity to marketing senior care programs. | Monitoring digital marketing campaign for on -going recruitment needs. 2023 will see shift to include client marketing now that wait list not an issue. • 2023 pitch of School program and Exhale project • Updating website to include partner/awards and video providing more robust place for potential hires to land • Ads and sponsorships in mental health related special sections and Chamber related activities
| Tactic 3.2.2: Development plan strategically and consistently engages contributors across multiple donor levels. | Financial metrics – grant funding, donor support | Val, Michelle, Magellan, Chair of Marketing & Development Committee | Q1 – 2023 | Completed. Plan in process of implementation | Plan completed and in process of implementation. Regular monthly Marketing & Development Meetings set out grant, town and donor relationships. On-Core Golf "Friend"raising event strategy in place. Town update letter in Spring and Summer Appeal to past donors. | Pursing OnCore Golf event with Marketing & Development team for Feb or March 2023 • Regular internal M & D meetings to select companies, grantors and individuals to develop relationships • Year End Appeal sent out – June select appeal to go out
Strategy 3.3: Organization is compliant with rules & regulations that govern operations and successfully manages the risk associated with service delivery. | Tactic 3.3.1: Identify and document procedures and processes to ensure on-going compliance. | Inventory of compliance requirements and documentation of processes. | Bev, Bonadio, BOD representative on Compliance Committee | Q4- 2021 | On track and on-going. Continue to partner with Bonadio as a resource | Conduct monthly compliance meetings to train on required elements of a compliance program – Policies and Procedures, Training and Development, Monitoring and Auditing, Enforcement and Corrective Actions • Responding to OMH/OIG comprehensive compliance plan updates o Each member of the committee is addressing a plan element or requirement such as reviewing our committee charter, policy review, privacy and security assessments, Audit Plan, Work Plan and Training Plan. o Conducting Agency-wide Annual Risk Assessment to manage risk exposure across all people and department and manage them well so that we can pursue our strategic goals and provide value. It is about identifying and taking sensible and proportionate measures to control risks. Leadership, risk and reputation are all linked in the life of a nonprofit. | To be updated
| Tactic 3.3.2: Identify appropriate levels of professional, general and BOD liability insurances. | Insurance levels are appropriate and optimal, policies are current and updated | Michelle | Q1 - 2022 | Completed and reviewed each year in Q1. | Review in process for Q1 2023 | To be revised in Q! 2023